WEEK 1 TASK

Data Analysis Strategy & Planning

Logistics Operations Analytics

Submission purpose A practical, audit-friendly plan for turning logistics transaction, inventory, transport and tracking data into measurable operational improvements. The plan separates descriptive, diagnostic, predictive and decision-support work.

Prepared for: Logistics Data Analysis Assignment
Planning horizon: Week 1 (32-hour research and planning allocation)
Document date: 30 August 2026

# 1. Technical Summary

The recommended strategy is to treat logistics analysis as an end-to-end performance system rather than a collection of isolated charts. The primary objective is to identify where service failures, delays, excess inventory and logistics cost originate; quantify their operational impact; and establish a repeatable KPI framework for daily and weekly decisions.

The first analytical focus should be delivery reliability and order-flow bottlenecks because these connect directly to customer service and can be decomposed into order creation, allocation, picking, packing, dispatch, transit, delivery and exception/return handling. Inventory health and logistics cost should be analyzed in parallel so improvements in one area do not create unacceptable trade-offs elsewhere.

Recommended analytical principle Do not optimize a single KPI in isolation. A reduction in delivery time is not a successful improvement if it materially increases freight cost, stockouts, damage, overtime or expedited shipments.

## Decision questions

Where and when are logistics delays occurring, and which process stages contribute most to total cycle time?

Which lanes, carriers, warehouses, customers, SKUs or order types have disproportionate failure rates?

How much inventory is available, where is it positioned, and where are stockouts or excess stock concentrated?

Which operational drivers are associated with higher cost per order, shipment or kilometre?

Which KPIs should be monitored daily, weekly and monthly, and what thresholds should trigger investigation?

What data-quality controls are required before management decisions can safely rely on the analysis?

# 2. Scope and Logistics Problem Definition

## 2.1 In-scope operational domains

| Domain | Core question | Primary data | Expected output |
| --- | --- | --- | --- |
| Order fulfilment | Why are orders late or incomplete? | Orders, status events, timestamps | Cycle-time decomposition, late-order drivers |
| Transport | Which lanes/carriers create delay or cost? | TMS, GPS, carrier invoices | Lane/carrier scorecards, transit analysis |
| Warehouse | Where do handling bottlenecks occur? | WMS scans, labour/activity logs | Pick/pack productivity, queue analysis |
| Inventory | Where are stockouts/excess stock occurring? | ERP/WMS inventory, receipts, demand | Inventory health and service-risk views |
| Exceptions | What causes failures, returns and damage? | Exception codes, claims, returns | Pareto of failure causes |

## 2.2 Out-of-scope for Week 1

Automated route optimization or vehicle-routing deployment.

Production machine-learning forecasting without validated historical data.

Real-time IoT architecture implementation.

Financial accounting reconciliation beyond logistics-related cost fields.

Causal claims requiring controlled experiments that are not supported by the available data.

## 2.3 Core analytical hypotheses

| ID | Hypothesis | Test approach |
| --- | --- | --- |
| H1 | Delivery lateness is concentrated in a small number of lanes, carriers, facilities or process stages. | Pareto analysis + stratified delay rates |
| H2 | High order cycle time is driven more by internal handling/waiting time than line-haul transit for some order segments. | Stage-duration decomposition |
| H3 | Stockouts and excess inventory are concentrated in a relatively small set of SKUs/locations. | ABC-style segmentation + inventory ageing |
| H4 | Higher logistics cost is associated with low load utilization, expedited shipping and poor lane/carrier performance. | Cost-driver analysis |
| H5 | A meaningful share of apparent operational problems are data-quality problems. | Data-quality profiling |

# 3. Proposed Analysis Process

The workflow is designed to be reproducible: every KPI should have a defined numerator, denominator, timestamp logic, inclusion rule and owner.

Figure 1. End-to-end logistics analysis process.

## 3.1 Step-by-step method

1. Frame the business question: Define the operational decision, affected process, unit of analysis, time horizon and success criteria.

2. Inventory data sources: Map systems, tables/files, owners, refresh frequency, primary keys and relationships.

3. Establish analytical grain: Decide whether the base unit is order, order line, shipment, package, inventory-day, SKU-location-day, trip or scan event.

4. Profile and validate data: Check completeness, uniqueness, validity, consistency, referential integrity and timestamp plausibility.

5. Build a canonical logistics dataset: Create standardized dimensions for date, facility, lane, carrier, SKU, customer segment and status/event types.

6. Calculate baseline KPIs: Establish current performance before attempting optimization.

7. Diagnose drivers: Segment performance and use Pareto, cohort, correlation and root-cause analysis.

8. Quantify business impact: Translate delay, stockout, excess inventory and damage into service and cost consequences where reliable cost data exists.

9. Visualize decision points: Create dashboards and exception views that tell users what changed, where, why and what needs action.

10. Recommend controls and next analyses: Define thresholds, ownership, monitoring cadence and follow-up modelling opportunities.

# 4. Data Sources and Data Architecture

## 4.1 Preferred internal sources

| Source | Useful fields | Analytical purpose |
| --- | --- | --- |
| ERP / Order Management | Order ID, order date, promised date, customer, SKU, quantity, priority, status | Order fulfilment and customer-service performance |
| WMS | Pick/pack timestamps, warehouse, bin/location, activity, inventory movements | Warehouse process efficiency and inventory movement |
| TMS / Carrier systems | Shipment ID, carrier, lane, dispatch, ETA, actual delivery, freight cost | Transport reliability and cost |
| GPS / Telematics | Vehicle location, trip start/end, distance, dwell and route events | Actual movement and dwell analysis |
| Inventory master | SKU, location, on-hand, reserved, damaged, safety stock, reorder point | Availability, ageing and stock-risk analysis |
| Procurement / Supplier data | PO dates, supplier, promised/actual receipt, quantity, purchase cost | Inbound reliability and supplier performance |
| Returns / Claims | Return reason, damage code, customer, shipment, resolution | Quality and failure analysis |
| External benchmark data | Country/region logistics benchmarks, macro conditions, public indicators | Context and benchmarking |

## 4.2 Public data for benchmarking

The World Bank Logistics Performance Index (LPI) is suitable for external logistics context. The current LPI 2.0 uses actual supply-chain tracking data and covers 2023–2024; the older survey-based LPI covers six dimensions including customs, infrastructure, logistics services, tracking/tracing and timeliness. It should be treated as contextual benchmarking rather than a substitute for company-level operational data.

World Bank LPI 2.0 — country-level supply-chain speed and connectivity indicators.

World Bank DataBank — historical LPI indicators and downloadable data.

Public shipment/order datasets — useful for practicing order-cycle, delivery-delay, inventory and exception analyses when company data is unavailable.

Data-source rule Internal operational systems should remain the primary source for company decisions. Public datasets are best used for methodology practice, benchmarking or scenario testing because definitions and data-generating processes may differ.

# 5. Analytical Data Model

A star-schema-style analytical model is recommended because logistics reporting repeatedly slices facts by time, location, carrier, SKU and customer.

| Table / layer | Example fields | Grain |
| --- | --- | --- |
| Fact_Order | order_id, order_date, promised_date, customer_id, status | One row per order |
| Fact_Order_Line | order_id, sku_id, ordered_qty, shipped_qty | One row per order line |
| Fact_Shipment | shipment_id, order_id, carrier_id, dispatch_ts, delivery_ts, cost | One row per shipment |
| Fact_Event | shipment_id/order_id, event_type, event_ts, facility_id | One row per operational event |
| Fact_Inventory_Daily | date, sku_id, location_id, on_hand, reserved, damaged | One row per SKU-location-day |
| Dim_Date | date, week, month, quarter, holiday flag | One row per date |
| Dim_Carrier | carrier_id, mode, service level | One row per carrier |
| Dim_Location | facility_id, city, region, facility_type | One row per location |
| Dim_SKU | sku_id, category, weight, volume, ABC class | One row per SKU |

## 5.1 Critical data-quality checks

Uniqueness: order, shipment and event identifiers meet expected uniqueness rules.

Completeness: promised date, dispatch time, delivery time, carrier, facility and quantity fields have monitored missingness.

Validity: dates follow plausible event order; quantities and costs respect business constraints.

Consistency: status codes, carrier names, facility IDs and SKU identifiers use controlled mappings.

Referential integrity: shipment records link to valid orders; order lines link to valid SKUs.

Outlier review: negative durations, extreme freight costs, impossible distances and duplicate scans require investigation.

Time-zone control: timestamps are normalized to a documented standard before duration calculations.

# 6. Analytical Methods

| Method | Use | Important control |
| --- | --- | --- |
| Descriptive analytics | What happened? Trends, distributions, rates, percentiles. | Define denominator and time window. |
| Diagnostic analytics | Where and why? Segmentation, Pareto, cohorts, stage decomposition. | Compare like-for-like segments. |
| Correlation / association | What variables move together? | Do not interpret correlation as causation. |
| Root-cause analysis | Which operational causes are actionable? | Validate exception codes with operations. |
| Forecasting (later phase) | What is likely to happen? | Backtest against historical periods. |
| Predictive modelling (later phase) | Which future cases are at risk? | Prevent target leakage; assess calibration. |
| Optimization (later phase) | What action best meets the objective? | Document constraints and objective function. |

# 7. KPI Framework

Figure 2. Balanced KPI framework for logistics operations.

| KPI | Definition | Cadence | Why it matters |
| --- | --- | --- | --- |
| On-Time Delivery (OTD) | Delivered on/before promised date ÷ eligible delivered orders | Daily/weekly | Service reliability |
| OTIF | Orders delivered on time and in full ÷ eligible orders | Weekly | Combined service performance |
| Order Cycle Time | Delivery timestamp − order timestamp | Daily/weekly | End-to-end speed |
| Pick/Pack Cycle Time | Pack completion − defined upstream stage timestamp | Daily | Warehouse bottleneck detection |
| Transit Time | Delivery − dispatch | Daily/weekly | Carrier/lane performance |
| Dwell Time | End of wait − start of wait | Daily | Facility/process bottlenecks |
| Fill Rate | Units shipped ÷ units ordered | Daily/weekly | Product availability |
| Stockout Rate | Stockout events ÷ demand opportunities | Daily/weekly | Inventory service risk |
| Inventory Accuracy | Correct inventory records ÷ audited records | Weekly/monthly | Stock integrity |
| Days of Inventory | Average inventory ÷ average daily demand | Weekly/monthly | Inventory efficiency |
| Freight Cost / Order | Attributable freight cost ÷ shipments/orders | Weekly/monthly | Transport economics |
| Cost / km | Freight cost ÷ transport distance | Weekly/monthly | Lane efficiency |
| Load Utilization | Used capacity ÷ available capacity | Daily/weekly | Asset utilization |
| Damage/Return Rate | Damaged/returned units or orders ÷ shipped units/orders | Weekly/monthly | Quality |
| Exception Rate | Shipments/orders with exception ÷ eligible shipments/orders | Daily/monthly | Operational stability |
| Data Completeness | Non-null critical records ÷ expected critical records | Daily | Analytics reliability |

## 7.1 KPI governance

Every KPI has a single written definition and accountable owner.

Denominators are explicit; rates without denominators are not decision-grade metrics.

Thresholds are based on historical baseline, contractual SLA, target state or statistical control limits.

KPI changes are version-controlled when business definitions change.

Dashboards separate current performance, trend, exceptions and root-cause drill-down.

# 8. Visualization and Dashboard Design

The dashboard should answer four questions in order: What changed? Where? Why? What action is required?

| View | Recommended visual | Decision supported |
| --- | --- | --- |
| Executive KPI scorecard | KPI cards + sparklines | Is service/cost/inventory performance on target? |
| Delay Pareto | Sorted bars + cumulative percentage | Which causes contribute most to delays? |
| Lane/carrier matrix | Heatmap | Which lanes/carriers require investigation? |
| Cycle-time decomposition | Stacked bar / box plot | Which process stage consumes time? |
| Inventory health | ABC segmentation + ageing chart | Where is stock risk or excess concentrated? |
| Exception monitoring | Action table with flags | Which individual shipments/orders need action? |
| Geographic view | Map when location granularity is reliable | Where are bottlenecks geographically? |

Visualization rule Use maps only when geography adds decision value. For most operational diagnosis, a sorted table, Pareto chart, box plot or heatmap is often more precise than a map.

# 9. Timeline and Milestones

The following is a realistic initial execution plan after Week 1. It can be compressed or extended depending on data access and system complexity.

| Period | Main work | Milestone |
| --- | --- | --- |
| Week 1 | Research, scope, KPI definitions, source inventory, analytical design | Approved analysis charter + KPI dictionary |
| Week 2 | Data extraction, profiling, cleaning and reconciliation | Validated analytical dataset v1 |
| Week 3 | Baseline descriptive analysis and segmentation | Baseline KPI pack + issue inventory |
| Week 4 | Diagnostic/root-cause analysis | Driver analysis + Pareto + bottleneck findings |
| Week 5 | Dashboard, recommendations and validation | Decision-ready dashboard + action plan |
| Week 6 | Monitoring controls, documentation and handover | Reusable pipeline/report + KPI governance |

## 9.1 Week 1 — 32-hour work allocation

| Activity | Hours |
| --- | --- |
| Research and domain understanding | 5 |
| Problem framing and scope | 4 |
| Data-source and data-model planning | 5 |
| KPI definition and governance design | 5 |
| Analytical-method selection | 4 |
| Visualization/dashboard planning | 3 |
| Timeline, risks and QA plan | 3 |
| Drafting, review and final formatting | 3 |
| Total | 32 |

# 10. Tools and Technology Stack

| Tool | Use cases | Role |
| --- | --- | --- |
| SQL | Extraction, joins, aggregation, KPI computation and transformations | Primary analytical query language |
| Python / pandas | Data profiling, statistics, automation and diagnostics | Repeatable analysis layer |
| Excel | Quick validation, reconciliation and business review | Stakeholder checking |
| Power BI / Tableau | Interactive dashboards and drill-downs | Presentation/monitoring layer |
| Git / version control | Track SQL, notebooks, definitions and changes | Reproducibility and auditability |
| Data warehouse / lakehouse | Centralized analytical storage | Scalable source of truth |

# 11. Risks, Limitations and Robustness Checks

| Risk | Why it matters | Mitigation |
| --- | --- | --- |
| Timestamp inconsistency | Different systems record different event times or time zones. | Normalize timestamps; document event definitions. |
| Selection bias | Only successful shipments or selected carriers appear. | Reconcile against source control totals. |
| Survivorship bias | Cancelled/failed/returned orders are excluded. | Retain relevant lifecycle statuses. |
| Metric gaming | Teams optimize the measured KPI instead of the objective. | Use balanced KPIs and guardrails. |
| Confounding | Distance, product type, service and carrier mix move together. | Use stratification and multivariable analysis. |
| Data leakage | Future information enters predictive features. | Freeze features at prediction time. |
| Definition drift | Business rules change over time. | Version KPI definitions. |
| Benchmark mismatch | Public data uses different populations/definitions. | Use external data for context only. |

## 11.1 Robustness checks

Recalculate KPIs using alternative reasonable inclusion rules to test sensitivity.

Compare mean, median and upper percentiles for cycle-time metrics; logistics durations are often right-skewed.

Check whether conclusions persist across major facilities, carriers, lanes and customer segments.

Reconcile aggregate totals to source-system control totals before publishing.

Validate surprising findings with operational SMEs and sample-level record review.

# 12. Expected Analytical Deliverables

| Deliverable | Minimum content |
| --- | --- |
| KPI dictionary | Metric definitions, formulas, filters, owners, cadence and thresholds. |
| Data inventory | Source systems, fields, keys, refresh frequency and data owner. |
| Data-quality report | Missingness, duplicates, invalid values, referential integrity and reconciliation. |
| Baseline analysis notebook / SQL | Reproducible calculations and documented assumptions. |
| Operational dashboard | KPI scorecard, trends, exceptions and drill-downs. |
| Root-cause analysis | Pareto of delay/exception causes and segment-level drivers. |
| Recommendation register | Finding → evidence → action → owner → expected impact → monitoring KPI. |

# 13. Recommended Next Steps

Confirm the exact logistics process being analyzed and define the primary decision owner.

Obtain sample extracts from order, shipment, warehouse and inventory systems covering several months if available.

Create the KPI dictionary before building the dashboard; dashboard formulas should not become undocumented business logic.

Perform data-quality profiling before interpreting operational trends.

Establish baseline OTD/OTIF, cycle time, fill rate, stockout rate and freight-cost metrics.

Use Pareto and segmentation to identify the small number of lanes, facilities, carriers, SKUs or causes responsible for the largest share of issues.

Validate findings against individual records and operational knowledge before recommending process changes.

Only after the baseline is trusted, proceed to predictive forecasting, delay-risk scoring or optimization.

# 14. Further Questions for the Business / Data Owner

What is the contractual definition of 'on time' for each service level?

Should OTD/OTIF exclude customer-caused delays, force majeure or cancelled orders?

Which timestamp is authoritative for dispatch and delivery?

Are freight costs available at shipment level, including fuel surcharges and accessorials?

How are split shipments and partial deliveries represented?

How is inventory reserved, damaged and in-transit stock represented?

Which exception codes are controlled and which are free-text?

What action is expected when a KPI crosses threshold?

Which systems are refreshed near real time versus batch?

Who owns each KPI and who is accountable for acting on exceptions?

# 15. Research Sources and References

World Bank (2023). Logistics Performance Index 2023 — Connecting to Compete: Trade Logistics in an Uncertain Global Economy.
https://www.worldbank.org/en/news/press-release/2023/04/21/world-bank-releases-logistics-performance-index-2023

World Bank DataBank. Logistics Performance Index dataset and metadata.
https://databank.worldbank.org/source/logistics-performance-index-%28lpi%29

World Bank. Logistics Performance Index 2.0 — methodology and current indicator framework.
https://lpi.worldbank.org/en/about

World Bank Data. Ability to track and trace consignments indicator.
https://data.worldbank.org/indicator/LP.LPI.TRAC.XQ

Oracle. SCM Analytics — examples of order fulfilment, delivery and inventory KPIs.
https://www.oracle.com/fusion-data-intelligence/scm-analytics/

Source-use note These sources support the planning framework and external benchmarking context. Company-level KPI targets should be derived from the organization's own historical performance, SLAs, cost structure and operating constraints rather than copied from public benchmarks.

# Appendix A — Example KPI Threshold Logic

| KPI | Green | Amber | Red / trigger |
| --- | --- | --- | --- |
| OTD | At/above target | Within agreed tolerance below target | Material breach or sustained decline |
| OTIF | At/above target | Small deviation | Sustained/material deviation |
| Cycle time | At/below target | Moderate increase | Large increase or high-tail deterioration |
| Stockout rate | Below target | Near threshold | Above threshold |
| Freight cost/order | At/below budget | Moderate variance | Material variance |
| Data completeness | ≥ agreed quality floor | Below floor but recoverable | Critical fields missing / pipeline unreliable |

Exact numerical thresholds should be established after baseline measurement and stakeholder agreement. Arbitrary targets before profiling the operation would create false precision.

# Appendix B — Definition of Done

Business question and scope are approved.

All primary data sources and owners are documented.

Analytical grain and join logic are documented.

Critical data-quality checks pass or exceptions are explicitly recorded.

KPI definitions have denominators and inclusion rules.

Baseline results reconcile to source-system totals.

Major findings have segment-level evidence and record-level validation.

Dashboard visuals are decision-oriented rather than decorative.

Limitations and non-causal interpretations are documented.

Recommendations identify an action, owner, expected impact and monitoring KPI.